## Campaigns
Area | Tasks | Start Date | Duration Days | End Date
Grand Opening | Teaser countdown on Instagram & TikTok (“something is spinning on Calle 72”) | 2027-01-04 | 14
| Press release to Bogotá food blogs and neighborhood groups | 2027-01-11 | 14
| Grand opening week: free soft drink with any Combo | 2027-01-18 | 7
| Flyers & free tastings at nearby offices and universities | 2027-01-18 | 14
| Announce the Customer Satisfaction Guarantee (counter signage + social post) | 2027-01-18 | 7
Digital Advertising | Always-on content on Instagram, TikTok & Facebook (product videos, behind the counter, combos) | 2027-01-04
| Google Business Profile: photos, hours, menu and review requests | 2027-01-04
| Paid geo-targeted Meta Ads (radius around the store) | 2027-01-18
| Food micro-influencer & blogger collaborations in Bogotá — wave 1 | 2027-02-01 | 28
| QR code on packaging and receipts: follow us + 10% off the next order | 2027-02-15
| WhatsApp Business catalog and weekly offer broadcast | 2027-02-22
| Monthly customer photo contest (#DonerHouse): winner gets a free Combo | 2027-04-05 | 182
| Food micro-influencer & blogger collaborations in Bogotá — wave 2 (second semester) | 2027-08-02 | 28
| TikTok challenge: “the perfect wrap” video with a prize | 2027-09-27 | 21
Delivery & Loyalty | Launch on Rappi, Uber Eats & DiDi Food with an introductory discount | 2027-01-25 | 28
| Loyalty card: every 10th döner is free | 2027-02-01
| Student & office-worker discount, first semester (10% with ID or work badge) | 2027-02-01 | 119
| Payday weekends (15th and 30th): Combo upgrade to the next size | 2027-03-01
| Corporate lunch plan: bulk orders for nearby offices via WhatsApp | 2027-03-15
| Refer-a-friend: both get free fries on their next order | 2027-04-12 | 84
| Student & office-worker discount, second semester (10% with ID or work badge) | 2027-08-02 | 119
| Rainy-season delivery push: free drink on delivery orders on rainy days | 2027-10-18 | 42
| Double loyalty stamps in December | 2027-12-06 | 21
Seasonal Dates | Valentine's Day (14 Feb): “Share a Döner”, 2 Combos with 20% off | 2027-02-08 | 7
| Mother's Day (9 May): Family Combo pack | 2027-05-03 | 7
| Father's Day (20 Jun): Large Döner Combo at a special price | 2027-06-14 | 7
| Six-month anniversary (4 Jul): free size upgrade all week | 2027-07-05 | 7
| Amor y Amistad (18 Sep): Friends Combo, 3 Combos with 15% off | 2027-09-13 | 7
| Long weekend (18 Oct): delivery-app free-fries promo | 2027-10-11 | 14
| Halloween (31 Oct): themed combo and social costume contest | 2027-10-25 | 7
| Long weekend (15 Nov): delivery-app free-fries promo | 2027-11-08 | 14
| Black Friday (26 Nov): one-day Combo deal, delivery apps and store | 2027-11-22 | 7
| Christmas & year-end: Party Pack for office and family gatherings | 2027-12-13 | 14
Community & Partnerships | First-semester welcome week: campus stand with free samples | 2027-02-01 | 7
| Partnerships with nearby gyms and coworking spaces (show your badge, get a Combo deal) | 2027-03-08 | 84
| Neighborhood tasting day: live döner-carving show on Calle 72 | 2027-05-17 | 7
| Second-semester welcome week: campus stand with free samples | 2027-08-02 | 7
| Sponsor a local amateur football tournament: team Combo packs | 2027-08-16 | 28
| Community giving: one döner donated to a local food bank for every 10 sold | 2027-10-04 | 28
Product & Menu | Customers vote on the next limited-edition sauce (Instagram Stories poll) | 2027-06-21 | 14
| Limited-edition spicy döner with the winning sauce | 2027-07-12 | 28
Low & Dead Season | Back-to-work office lunch Combo (January, offices reopen before universities) | 2027-01-04 | 21
| Holy Week (22–28 Mar), dead season: “stay-in” delivery Combo for two | 2027-03-22 | 7
| Mid-year school and university break: free delivery on orders over COP $40,000 | 2027-06-21 | 21
| Mid-year holidays, dead season: “stay-in” delivery Combo for two | 2027-06-28 | 14
| Weekday Happy Hour (3–5 PM): discounted Combo to fill the slow weeks | 2027-07-12 | 21
| Gift vouchers for Christmas, redeemable in January | 2027-11-29 | 21
START STRATEGIES
END STRATEGIES |  | 2027-12-31
Notes:
Blue = editable inputs (start dates, fixed durations, end of strategies). Black = formulas. End Date = Start Date + Duration Days.
Plan covers all of 2027 (January to December). Every start date is a Monday and fixed durations are whole weeks (multiples of 7 days).
Always-on campaigns have no fixed length: their duration runs from their start date to END STRATEGIES (cell C52).
Assumption: the store opens in the first week of January 2027. If the opening date moves, shift every start date by the same number of days.
Assumption: discounts (10% student/office, 10th döner free, COP $40,000 free-delivery minimum, Party Pack, etc.) are proposals, not survey results. They were sized to stay above production cost at the 35% target margin (website, section 3.4.2).
Seasonal dates 2027: Valentine's Day 14 Feb, Holy Week 22-28 Mar, Mother's Day 9 May, Father's Day 20 Jun, Six-month anniversary 4 Jul, Amor y Amistad 18 Sep, long weekends 18 Oct and 15 Nov, Halloween 31 Oct, Black Friday 26 Nov.
The Gantt chart with the season colors is on the next sheet, 'Gantt Chart'; it reads the dates from this table.

## Gantt Chart
Area | Campaign | Start | End | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December
 | time axis 2027-01-04 to 2027-12-27
Season of each week (editable) |  |  |  | Low | Low | Low | Low | High | High | High | High | High | High | High | Dead | High | High | High | High | High | High | High | High | High | High | Low | Low | Low | Dead | Dead | Low | Low | Low | High | High | High | High | High | High | High | High | High | High | High | High | High | High | High | High | High | Low | Low | Low | Dead | Dead
Grand Opening
Digital Advertising
Delivery & Loyalty
Seasonal Dates
Community & Partnerships
Product & Menu
Low & Dead Season
Legend
High season (34 weeks)
Low season (13 weeks)
Dead season (5 weeks)
Solid bar = campaign running that week; its color is the season of that week. Pale color = season of the weeks where the campaign is not running.
The Season row (row 3) is editable: type High, Low or Dead in any week and the whole chart recolors. Campaign names and dates are read from the 'Campaigns' sheet.
Assumption: seasons follow Bogotá's academic and holiday calendar for a store serving students and office workers (they are not measured sales). High = semesters in session; Low = post-holiday, exam and between-semester weeks and year-end wind-down; Dead = Holy Week, mid-year holidays, Christmas-New Year.